## Sheet1
450 Murray Hill - 9/1/2022 Site Visit
Item # | Description | Corresponding Picture #
1 | Montalto to start loading dock construction | IMG_3679, IMG_3700, IMG_3726
2 | Well to be capped | IMG_3693
3 | Spray for weeds on pavement outside D2 | IMG_3702
4 | Repair or patch broken pipe / roof drain outside D2 | IMG_3704
5 | Roof drain cover outside unit D2 should be removed/eliminated (for next year) | IMG_3703
6 | Patch the D2 landing/limestone | IMG_3705
7 | Repave entire "North Lot" (multiple holes, damage throughout). Check drawings to calculate square footage | IMG_3694, IMG_3695, IMG_3708
8 | Repair or patch broken pipe / roof drain outside Unit D | IMG_3709
9 | Paint and caulk around doors of Unit D | IMG_3711
10 | Albert to send text about trucks parked outside Unit E (for towing?)
11 | Repairs required along concete wall and pavement dropoff outside E1. Extend guard railing appx 32 feet | IMG_3714
12 | Holes marked outside E1 - for future repair | IMG_3713, IMG_3712
13 | Contact East Rutherford DPW to fix potholes and street damage along Madison Cir Drive | IMG_3717, IMG_3721
14 | Report derelict trucks along Madison Cir Drive | IMG_3718
15 | Remove section of guardrail outside Unit C | IMG_3719
16 | Sasha to trim hedges and evergreens encroaching onto sidewalk in front of Unit A and A1 | IMG_3722
17 | Remove five dead trees in front of building along Murray Hill Pkwy | IMG_3723
18 | Restripe parking at front sidewalk entrance so cars will not park there and block entrance | IMG_3725
Other notes
a | Property was last paved about 20 years ago