## Sheet1
525 Main - 9/2/2022 Site Visit
Item # | Description | Corresponding Picture #
1 | Unit 1 drain in interior loading dock is clogged. Need to snake drain
2 | Stripe lines leading up to Unit 1 loading dock
3 | Leak outside drip system at Unit 2 | IMG_3760
4 | Need to check all drip irrigation hoses for leaks (Carlos). Remove all weed cloth/fabric | IMG_3759
5 | Another broken sprinkler outside Unit 2 loading dock | IMG_3761
6 | Dead trees on north of property | IMG_3762
7 | Straighten parking signs - pour concrete if needed | IMG_3763
8 | Seal coat and restripe north lot outside Unit 1 and Unit 2 | IMG_3765
9 | Spray for weeds in the lot | IMG_3766
10 | Crack fill entire post office lot | IMG_3768
11 | Notify 4A tenants to remove debris in front of loading docks | IMG_3769
Other notes
a