## Sheet1
969 Newark Tunpike - 9/2/2022 Site Visit
Item # | Description | Corresponding Picture #
1 | Need Jeff Boyer to straighten pole with mounted camera. Possibly cover exposed wires with conduit and metal box. | IMG_3728, IMG_3729
2 | Remove all trees at entrance of property. Trees currently obstructing view of security camera. | IMG_3730
3 | Update directory (Tim). Contact signs by Linn.
4 | Trim/prune trees near loading dock | IMG_3731
5 | Possibly extend upwards cameras to have a better view over trailors (extend up 3 feet) | IMG_3732
6 | Stolen cameras - Need to construct 25ft post (overall height) + two cameras on top. John H to perform work. Pole to be located on north side of shed - between shed and property line of coffin blocks. | IMG_3733, IMG_3734
7 | Need to follow up with Coppers Creek (?) - neighboring property wants to run two 6" sewer mains through property. We are asking them to reroute them through the back of the property
8 | Remove dead tree in front of property on Newark Turnpike | IMG_3736
9 | Need to provide some roof maintenance - minor spot repairs and clean drains (no pic)
10 | Family foods planning to move into Cooper Electric? What is the status of this? Get update from Monte
11 | Add flag to post | IMG_3737
12 | Restripe for additional parking outside Cooper Electric | IMG_3739
13 | Create road through corner (remove coffin blocks) for easier vehicle access | IMG_3740
14 | Spot pavement repairs (marked) | IMG_3741
15 | Seal coat and restripe south lot | IMG_3752, IMG_3753, IMG_3754, IMG_3756
16 | Additional pavement repairs on east side of building | IMG_3742
17 | Plan for additional striping/parking outside Family Foods and Overseas Moving (east side of building) | IMG_3743
18 | Clean drainage area on east side of property | IMG_3745
19 | Pruning required on east side of property | IMG_3746
20 | Phil needs to put continued pressure on Veola Water - resolution for water main break
21 | Seal north lot - call Swan Seal Coating | IMG_3748, IMG_3749
22 | Provide Albert with map of 42 truck parking spots on west lot (leased parking)
23 | Boyer to inspect pump outside Panamerican loading dock | IMG_3750
Other notes
a